## Sprint 1
Sprint Burndown Chart
Sprint 1
Task ID | Task Description | Initial Estimate | 13/oct./24 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Clone World Edit Repo | bar: Day 0 to Day 1
2 | Configure the development environment for all team members | Day 0: 3; Day 1: 1; Day 3: 1.5; Day 6: 0.5
3
4
5
6
7
8
9
10
11
12
13
14
Completed Effort |  | 0 | 2 | 0 | 1.5 | 0 | 0 | 0.5 | 0
Remaining Effort |  | 4 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0 | 0
Ideal Burndown |  | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0

## Sprint 2
Sprint Burndown Chart
Sprint 2
Task ID | Task Description | Initial Estimate | 20/oct./24 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Create User Stories | 6 | 1 | 2 |  |  | 1.5 |  | 1.5
2 | Understand WorldEdit commands and functionality | 15 | 1 | 1.5 |  | 3 | 2.5 | 2 | 5
3
4
5
6
7
8
9
10
11
12
13
14
Completed Effort |  | 0 | 2 | 3.5 | 0 | 3 | 4 | 2 | 6.5
Remaining Effort |  | 21 | 19 | 15.5 | 15.5 | 12.5 | 8.5 | 6.5 | 0
Ideal Burndown |  | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0

## Sprint 3
Sprint Burndown Chart
Sprint 3
Task ID | Task Description | Initial Estimate | 27/oct./24 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Find code smells | Day 0: 12; Day 6: 2
2 | Find use cases | Day 0: 6
3 | Find design patterns | Day 0: 18
4 | Analyse metrics | Day 0: 6
5
6
7
8
9
10
11
12
13
14
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Remaining Effort |  | 42 | 42 | 42 | 42 | 42 | 42 | 40 | 40
Ideal Burndown |  | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0

## Sprint 4
Sprint Burndown Chart
Sprint 4
Task ID | Task Description | Initial Estimate | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Find code smells | 10 |  |  |  | 2 | 1 | 3 | 4
2 | Find use cases | Day 0: 6
3 | Find design patterns | 18 | 3 | 5 |  | 5 | 2 | 2 | 1
4 | Analyse metrics | Day 0: 6; Day 4: 1
5 | Review peer code smeels | Day 0: 6
6 | Review peer use cases | Day 0: 6
7 | Review peer design patterns | Day 0: 6; Day 5: 1; Day 6: 2
8 | Review peer metrics | Day 0: 6
9
10
11
12
13
14
Completed Effort |  | 0 | 3 | 5 | 0 | 8 | 4 | 7 | 5
Remaining Effort |  | 64 | 61 | 56 | 56 | 48 | 44 | 37 | 32
Ideal Burndown |  | 64 | 54.8571 | 45.7143 | 36.5714 | 27.4286 | 18.2857 | 9.1429 | 0

## Sprint 5
Sprint Burndown Chart
Sprint 5
Task ID | Task Description | Initial Estimate | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Find use cases | Day 0: 6; Day 2: 1; Day 3: 4; Day 4: 1
2 | Analyse metrics | Day 0: 5; Day 2: 1; Day 4: 4
3 | Review peer code smells | Day 0: 6; Day 1: 3; Day 2: 1; Day 4: 2
4 | Review peer use cases | Day 0: 6; Day 3: 2; Day 4: 4
5 | Review peer design patterns | Day 0: 3; Day 1: 1; Day 2: 1; Day 3: 1
6 | Review peer metrics | Day 0: 6; Day 3: 2; Day 4: 2
7
8
9
10
11
12
13
14
Completed Effort |  | 0 | 4 | 4 | 9 | 13 | 0 | 0 | 0
Remaining Effort |  | 32 | 28 | 24 | 15 | 2 | 2 | 2 | 2
Ideal Burndown |  | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0

## Sprint 6
Sprint Burndown Chart
Sprint 6
Task ID | Task Description | Initial Estimate | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Analyse metrics | Day 0: 5
2 | Review peer metrics | Day 0: 6
3 | Explain design patterns | Day 0: 3; Day 1: 0.5; Day 3: 0.5
4 | Explain code smells | Day 0: 3; Day 1: 1
5 | Register rebrush command | Day 0: 0.5; Day 5: 0.5
6 | Implement selectable structure on click | Day 0: 5; Day 3: 0.5; Day 6: 1.5; Day 7: 3
7 | Implement the Screen for Brush Selection | Day 0: 5; Day 1: 2; Day 4: 1; Day 6: 2
8 | Implement a PreviewManager class to handle confirm or cancel | Day 0: 2; Day 1: 1; Day 5: 1
9 | Modify the BrushTool class to incorporate a way to show preview by a toggle | Day 0: 3; Day 1: 1; Day 5: 1; Day 7: 1
10 | Create a preview command on the BrushCommand class | Day 0: 2; Day 1: 2
11 | Implement Dropdown Buttons | Day 0: 3; Day 6: 2; Day 7: 1
12 | Understand the Fabric API | Day 0: 3; Day 1: 1; Day 2: 2
13
14
Completed Effort |  | 0 | 8.5 | 2 | 1 | 1 | 2.5 | 5.5 | 5
Remaining Effort |  | 40.5 | 32 | 30 | 29 | 28 | 25.5 | 20 | 15
Ideal Burndown |  | 40.5 | 34.7143 | 28.9286 | 23.1429 | 17.3571 | 11.5714 | 5.7857 | 0

## Sprint 7
Explain design patterns
Sprint Burndown Chart
Sprint 7
| Task ID | Task Description | Initial Estimate | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 1 | Implement Scrollbar | Day 0: 6; Day 5: 3
| 2 | Explain code smells | Day 0: 2
| 3 | Fix rebrush undo and redo | Day 0: 2; Day 4: 1; Day 5: 1
| 4 | Implement selected structure resizing | Day 0: 6; Day 1: 2.5; Day 4: 3; Day 5: 0.5
| 5 | Refactor preview logic to work with LocalSession | Day 0: 5; Day 1: 1; Day 3: 1; Day 5: 1
| 6 | Change BrushCommand commands to call the preview method | Day 0: 4; Day 2: 2; Day 3: 1; Day 4: 1
| 7 | Render preview based on the Player | Day 0: 2
| 8 | Create a Screen for each command | Day 0: 4; Day 2: 2
| 9 | Apply the Brush using the Command Screen | Day 0: 6; Day 6: 3
10
11
12
| Completed Effort |  | 0 | 3.5 | 4 | 2 | 5 | 5.5 | 3 | 0
| Remaining Effort |  | 37 | 33.5 | 29.5 | 27.5 | 22.5 | 17 | 14 | 14
| Ideal Burndown |  | 37 | 31.7143 | 26.4286 | 21.1429 | 15.8571 | 10.5714 | 5.2857 | 0

## Sprint 8
Sprint Burndown Chart
Sprint 8
Task ID | Task Description | Initial Estimate | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | Analyse metrics | 5 |  |  | 1 | 1 |  | 2
2 | Review peer metrics | 6 | 1 |  | 2 | 2 | 3 | 1
3 | Implement Scrollbar | 3 |  | 2 | 1
5 | Refactor preview logic to work with LocalSession | 2 |  |  | 3
6 | Apply the Brush using the Command Screen | 3 |  |  | 2
7 | Create a Screen for each command | 2 |  | 2
8 | Refactor Selectable structure feature | 3 | 2 |  |  | 1
9 | Modify the preview logic to work with Fabric | 3 | 2 | 1
10 | Fix bug (multiple previews rendered at once) | 4 | 3 | 1
11 | Search for a way to detect the exact player position | 1 |  |  |  | 1
12 | Refactor the preview undo | 1 |  | 1
13 | Fix brush preview hierarchy logic | 5 |  | 1 | 2 | 1
14 | Fix structure selection after using rebrush on a structure | 3 | 2 |  | 4 | 2 |  | 3
16 | Use Cases for each feature | 5 |  |  | 1 | 1 |  | 3
17 | Create the videos for each feature | 1 | [5 empty] | 1
Completed Effort |  | 0 | 10 | 8 | 15 | 8 | 3 | 6
Remaining Effort |  | 47 | 37 | 29 | 14 | 6 | 3 | -3
Ideal Burndown |  | 47 | 39.1667 | 31.3333 | 23.5 | 15.6667 | 7.8333 | 0