## Sprint 8
Sprint Burndown Chart
Sprint 8
Task ID | Task Description | Initial Estimate | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | Analyse metrics | 5 |  |  | 1 | 1 |  | 2
2 | Review peer metrics | 6 | 1 |  | 2 | 2 | 3 | 1
3 | Implement Scrollbar | 3 |  | 2 | 1
5 | Refactor preview logic to work with LocalSession | 2 |  |  | 3
6 | Apply the Brush using the Command Screen | 3 |  |  | 2
7 | Create a Screen for each command | 2 |  | 2
8 | Refactor Selectable structure feature | 3 | 2 |  |  | 1
9 | Modify the preview logic to work with Fabric | 3 | 2 | 1
10 | Fix bug (multiple previews rendered at once) | 4 | 3 | 1
11 | Search for a way to detect the exact player position | 1 |  |  |  | 1
12 | Refactor the preview undo | 1 |  | 1
13 | Fix brush preview hierarchy logic | 5 |  | 1 | 2 | 1
14 | Fix structure selection after using rebrush on a structure | 3 | 2 |  | 4 | 2 |  | 3
16 | Use Cases for each feature | 5 |  |  | 1 | 1 |  | 3
17 | Create the videos for each feature | 1 | [5 empty] | 1
Completed Effort |  | 0 | 10 | 8 | 15 | 8 | 3 | 6
Remaining Effort |  | 47 | 37 | 29 | 14 | 6 | 3 | -3
Ideal Burndown |  | 47 | 39.1667 | 31.3333 | 23.5 | 15.6667 | 7.8333 | 0