## Sprint 4
Sprint Burndown Chart
Sprint 4
Task ID | Task Description | Initial Estimate | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Find code smells | 10 |  |  |  | 2 | 1 | 3 | 4
2 | Find use cases | Day 0: 6
3 | Find design patterns | 18 | 3 | 5 |  | 5 | 2 | 2 | 1
4 | Analyse metrics | Day 0: 6; Day 4: 1
5 | Review peer code smeels | Day 0: 6
6 | Review peer use cases | Day 0: 6
7 | Review peer design patterns | Day 0: 6; Day 5: 1; Day 6: 2
8 | Review peer metrics | Day 0: 6
9
10
11
12
13
14
Completed Effort |  | 0 | 3 | 5 | 0 | 8 | 4 | 7 | 5
Remaining Effort |  | 64 | 61 | 56 | 56 | 48 | 44 | 37 | 32
Ideal Burndown |  | 64 | 54.8571 | 45.7143 | 36.5714 | 27.4286 | 18.2857 | 9.1429 | 0