## Sprint 7
Sprint Burndown Chart
Sprint 7
Task ID | Task Description | Initial Estimate | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Implement Scrollbar | Day 0: 6; Day 5: 3
2 | Explain code smells | Day 0: 2
3 | Fix rebrush undo and redo | Day 0: 2; Day 4: 1; Day 5: 1
4 | Implement selected structure resizing | Day 0: 6; Day 1: 2.5; Day 4: 3; Day 5: 0.5
5 | Refactor preview logic to work with LocalSession | Day 0: 5; Day 1: 1; Day 3: 1; Day 5: 1
6 | Change BrushCommand commands to call the preview method | Day 0: 4; Day 2: 2; Day 3: 1; Day 4: 1
7 | Render preview based on the Player | Day 0: 2
8 | Create a Screen for each command | Day 0: 4; Day 2: 2
9 | Apply the Brush using the Command Screen | Day 0: 6; Day 6: 3
10
11
12
Completed Effort |  | 0 | 3.5 | 4 | 2 | 5 | 5.5 | 3 | 0
Remaining Effort |  | 37 | 33.5 | 29.5 | 27.5 | 22.5 | 17 | 14 | 14
Ideal Burndown |  | 37 | 31.7143 | 26.4286 | 21.1429 | 15.8571 | 10.5714 | 5.2857 | 0